## Sheet1
ID | 1 | Description:
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "Date Of Birth" field do not accept dates before 1/1/2010, and accepts dates from future.
Severity | 2 | SInce it is not mandatory field, severity is not critical. It is high. Form can still work without this field but this field alone do not work with most valid imputs.
Priority | High | Field is often used, so priority is high.
Description | Field "Date Of Birth" should accept dates from 1/1/1900 to today's datum. Instead, field accepts dates only from 1/1/2010. Also, error message "Date Of Birth must be between 1/1/2010 and 1/1/2030." is written under field.
1.Enter "1/1/1900" in "Date Of Birth" field 2.Click on "Preffered contact" field
Expected result | "1/1/1900" is displayed in "Date Of Birth" field
Actual result | "1/1/1900" is displayed in "Date Of Birth" field and error message: "Date Of Birth must be between 1/1/2010 and 1/1/2030." is written under "Date Of Birth" field.
ID | 2
Browser | Google chrome
Operating system | Windows 10
Testing | Manual
Name | Error message is displayed under "Last name" field even though valid data is inserted
Severity | 4 | Error message do not affect form funcionality, so severity is low.
Priority | High | Field is used often, so priority is high.
Description | Error message "Lastname is required" is displayed under "Last name" field even though valid data is inserted.
Steps to reproduce | 1.Open “Create new” form 2.Enter “A” in “Last name” field 3.Click on “SSN” field
Expected result | "A" is diplayed in "Last name" field.
Actual result | "A" is diplayed in "Last name" field and error message "Lastname is required" is displayed under "Last name" field
ID | 3
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "Last name" field accepts invalid data.
Severity | 3 | Severity is medium, not high, because entering invalid data do not affect overall form funcionality and field works with valid imputs, but still, incorect data can make administration problems.
Priority | High | Field is used often, so priority is high.
Description | "Last name" field should only accepts letters, but it accepts numbers and special characters and do not provide error message.
Steps to reproduce | 1.Open "Create new" form 2.Enter "A" in "First Name" field 3.Enter (eg. "5", "#", ":", " ") in "Last Name" field 4.Click on "SSN" field
Expected result | "Last Name must only contain letters." message with red background is shown under "Last Name" field.
Actual result | Message is not displayed under "Last Name" field.
ID | 4
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "SSN" field accepts invalid inputs.
Severity | 3 | Severity is medium, not high, because entering invalid data do not affect overall form funcionality and field works with valid imputs, but still, incorect data can make administration problems.
Priority | High | Field is used often, so priority is high.
Description | "SSN" field should only accept 9 digits or remain empty. But, field accepts letters and accepts input format longer and shorter than 9 characters.
Steps to reproduce | 1.Open "Create new" form 2.Enter (eg. "789456123" ,"1", "pppkkkddd", "P", "$") in "SSN" field 3.Click on "Address Line 1" field
Expected result | Message "SSN field must contain 9 letters or remain empty." with red background has appeared under "SSN" field
Actual result | Error message "SSN field must contain 9 letters or remain empty." has not appeared under "SSN" field.
ID | 5
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "Date Of Birth" accepts dates outside the maximum bounary value.
Severity | 3 | Severity is medium, not high, because entering invalid data do not affect overall form funcionality and field works with valid imputs, , but still, incorect data can make administration problems.
Priority | High | Field is used often, so priority is high.
Description | "Date Of Brith" field should only accept dates from 1/1/1900 up to today's datum, but it accepts dates from future.
Steps to reproduce | 1.Open "Create new" form 2.Enter tommorow's datum in "Date Of Birth" field 3.Click on "SSN" field
Expected result | Message: "Date Of Birth must be between 1/1/1900 and today's date" with red background is shown under "Date of Birth" field.
Actual result | Error message has not appeared. Field has accepted date from future.
ID | 6
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "Date Of death" accepts dates outside the maximum bounary value.
Severity | 3 | Severity is medium, not high, because entering invalid data do not affect overall form funcionality and field works with valid imputs, but still, incorect data can make administration problems.
Priority | Medium | Field is less used, so priority is medium.
Description | "Date Of death" field should only accept dates from 1/1/2010 up to today's datum, but it accepts dates from future.
Steps to reproduce | 1.Open "Create new" form 2.Enter tommorow's datum in "Date Of death" field 3.Click on "SSN" field
Expected result | Message: "Date Of death must be between 1/1/2010 and today's date" with red background is shown under "Date of Birth" field.
Actual result | Error message has not appeared. Field has accepted date from future.
ID | 7
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "Email" field accepts incorect email form
Severity | 3 | Severity is medium, not high, because entering invalid data do not affect overall form funcionality and field works with valid imputs,but still, incorect data can make administration problems.
Priority | High | Field is used often, so priority is high.
Description | "Email" field accepts incorect email form
Steps to reproduce | Open "Create new" form Enter (eg. "a.co", "a@b", "a@", "@.com", "abcf@gm_com", ".k@gm.com"), in "Email" field Click on "Username" field
Expected result | Message: "Incorect Email form" with red background is displayed under "Email" field.
Actual result | Error message has not appeared. Field has accepted invalid email form.
ID | 8
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | “Patient Photo” field allows uploading files with invalid format.
Severity | 3 | Severity is medium, not high, because entering invalid data do not affect overall form funcionality and field works with valid imputs, but still, incorect data can make administration problems.
Priority | Medium | Field is less used, so priority is medium.
Description | “Patient Photo” field should only accept files with picture formats(eg. .jpg , .png), but it accepts all formats.
Steps to reproduce | Open "Create new" form Click on "upload" button In "open" window select "test.xml:" file, located on desktop and click "open" button.
Expected result | Message: "Only image formats are supported" appeared under "Patient photo" upload section
Actual result | Invalid format file is successifuly uploaded. Error message has not appeared.
ID | 9
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | "Adress Information" field name is spelled wrong
Severity | 4 | This defect do not affect form funcionality.
Priority | High | Visible to all users every time, so priority is high.
Description | "Adress Information" field should be spelled "Address Information"
Steps to reproduce | Open "Create new" form Check spellng of "Adress Information" text
Expected result | "Address Information" is written
Actual result | "Adress Information" is written
ID | 10
Browser | Google Chrome
Operating system | Windows 10
Testing | Manual
Name | Words missing capital letters.
Severity | 4 | This defect do not affect form funcionality.
Priority | High | Visible to all users every time, so priority is high.
Description | Words "death" in "Date Of death" field and words "maritial status" missing capital letters, so that they stand out from other words. All other words have capital letter.
Steps to reproduce | Open "Create new" form Check the capital letters of words.
Expected result | All field names have capital letters.
Actual result | Words "death" in "Date Of death" field and words "maritial status" missing capital letters